## Sheet1
[9 empty] | WEEK 1 | [6 empty] | WEEK 2 | [6 empty] | WEEK 3 | [6 empty] | WEEK 4 | [6 empty] | WEEK 5
|  | Copywriter | Vis. designer | Front-End | Back-End | UI design | Total days | Crit. part days | M | T | W | TH | F | SA | SU | M | T | W | TH | F | SA | SU | M | T | W | TH | F | SA | SU | M | T | W | TH | F | SA | SU | M | T | W | TH | F | SA | SU
Research + content production | [7 empty] | 7 | bar: WEEK 1 M to WEEK 1 F; WEEK 2 M to WEEK 2 T
Deciding design and produce template | [7 empty] | 2 | bar: WEEK 2 TH to WEEK 2 F
Create prod info / prod sale website | [7 empty] | 2 | bar: WEEK 3 M to WEEK 3 T
Create contact website | [7 empty] | 4 | bar: WEEK 3 M to WEEK 3 TH
Create order website | [7 empty] | 6 | bar: WEEK 3 W to WEEK 3 TH; WEEK 4 M to WEEK 4 TH
Finalize purchase solution | [7 empty] | 3 | bar: WEEK 4 TH to WEEK 4 F; WEEK 5 M
Identify elements, research |  | 7 |  |  |  |  | 7 | bar: WEEK 1 M to WEEK 1 F; WEEK 2 M to WEEK 2 T
Research and photograph |  |  | 7 |  |  |  | 7 | bar: WEEK 1 M to WEEK 1 F; WEEK 2 M to WEEK 2 T
Research retailer info & pos, create website w/map for locations. |  |  |  | 2 |  |  | 2 | bar: WEEK 2 M to WEEK 2 T
Identify interactions and structurise | [5 empty] | 7 | 7 |  | WEEK 2 TH: CUSTOMER MEETING
Create website main page template |  |  |  | 2 |  |  | 2 | bar: WEEK 2 TH to WEEK 2 F
Set up structure for customer interaction with products | [5 empty] | 1 | 1 | bar: WEEK 2 F
Decide visual appeal for product presentation |  |  | 1 |  |  |  | 1 | bar: WEEK 2 F
Create website "info about prod process" + "prod presentation and prizing" |  |  |  | 2 |  |  | 2 | bar: WEEK 3 M to WEEK 3 T
Create F.A.Q. to answer the most common questions |  | 2 |  |  |  |  | 2 | bar: WEEK 3 M to WEEK 3 T
Decide whats needed in contact form | [5 empty] | 1 | 1 | bar: WEEK 3 M
Set up servers and DB's for contact form |  |  |  |  | 2 |  | 2 | bar: WEEK 3 M to WEEK 3 T
Create website for contact, including a contact form |  |  |  | 2 |  |  | 2 | bar: WEEK 3 W to WEEK 3 TH
Find best way to solve "allways one click away from order page" | [5 empty] | 1 | 1 | bar: WEEK 3 W
Create form UI. Be able to order without making an user | [5 empty] | 1 | 1 |  | WEEK 3 SA: CUSTOMER MEETING
Set up server and DB's for form handling and processing |  |  |  |  | 3 |  | 3 | bar: WEEK 3 W to WEEK 3 TH; WEEK 4 M
Create the form as made by UI designer |  |  |  | 1 |  |  | 1 | bar: WEEK 4 M
Create website with form ordering, make it mobile friendly |  |  |  | 3 |  |  | 3 | bar: WEEK 4 T to WEEK 4 TH
Research payment options |  |  |  |  | 1 |  | 1 | bar: WEEK 4 TH
Research payment options |  |  |  | 1 |  |  | 1 | bar: WEEK 4 F
Create order page, make sure there's order confirmation |  |  |  | 1 |  |  | 1 |  | WEEK 5 W: CUSTOMER MEETING / PRESENTATION
Assist Front-End with purchase and set up server and DB's |  |  |  |  | 2 |  | 2 | bar: WEEK 4 F; WEEK 5 M
Days summed | [6 empty] | 50 | 24 | WEEK 5 T: RELEASE WEEK
Copywriter |  | 9
Visual designer |  |  | 8
Front-End developer |  |  |  | 14
Back-End developer |  |  |  |  | 8
UI designer | [5 empty] | 11
Cost each day, per person:
600NOK / HR * 7,5 = 4500,-
Total price: | 225000